## Sprint i
ID | User Story | Story Tasks | Sprint Number | Sprint Goal | Story Type | Story Points | Story Points Completed | Names and Contribution Percentage
1 | As a user I want to be able to create separate folders within the application so that I can put certain events/plans in specific categories. | -Code a list class-Create UI-Save lists to phone and databasse- | 1--3 | Environment Creation | F(T) | 3 | 1.5 | Eli Story: 25% (Knowledge Acquisition, Implementation) Brody Looney: 25% (Knowledge Acquisition) Callie Samson: 25% (Knowledge Acquisition) Finn Jacobs: 25% (Knowledge Acquisition)
2 | As a user I would like to have a username and password for my application so that my information within the application is secure. | -Code login functionality-Research password hashing-Research Google Login-Create UI-forget password research | 1--2 | Login System Creation | NF(T, KA) | 2 | 2 | Eli Story: 60% (Implementation) Brody Looney: 10% (Knowledge Acquisition) Callie Samson: 10% (Knowledge Acquisition) Finn Jacobs: 10% (Knowledge Acquisition)
5 | As a user I want to be able to delete entries from my bucket list so that I only see entries that resonate with me. | Add removed tag to entries or delete from phone and database-Create UI | 2--3 | Implement New Folder Modification Method | F(T) | 1 | 0.25 | Eli Story: 25% (Knowledge Acquisition) Brody Looney: 25% (Knowledge Acquisition) Callie Samson: 25% (Knowledge Acquisition) Finn Jacobs: 25% (Knowledge Acquisition)
16 | As a user I want to be able to add a deadline to an entry so that I am motivated to complete the task. | -Create UI-Research Notifications-Code Notifications-Create UI-Create deadline in entry class | 2--3 | Create a Deadline in the Entry Class | F(T, KA) | 1 | 0.25 | Eli Story: 25% (Knowledge Acquisition) Brody Looney: 25% (Knowledge Acquisition) Callie Samson: 25% (Knowledge Acquisition) Finn Jacobs: 25% (Knowledge Acquisition)
7 | As a user I want to be able to sort my entries based on priority so that I know which entries I would like to complete first. | -Create UI-Add priority to entry class-Code sort- | 3 | Add Folder Modification, Implement Task Sorting System | F(T) | 2 | 0.25 | Eli Story: 30% (Knowledge Acquisition) Brody Looney: 30% (Knowledge Acquisition) Callie Samson: 20% (Knowledge Acquisition) Finn Jacobs: 20% (Knowledge Acquisition)