## Sprint i
ID | User Story | Story Tasks | Sprint Number | Sprint Goal | Story Type | Story Points | Story Points Completed | Names and Contribution Percentage
1 | As a user I want to be able to create separate folders within the application so that I can put certain events/plans in specific categories. | -Code a list class-Create UI-Save lists to phone and databasse- | 1--4 | Environment Creation | F(T) | 3 | 3 | Eli Story: 100% (Knowledge Acquisition, Implementation) Brody Looney: 25% (Knowledge Acquisition) Callie Samson: 25% (Knowledge Acquisition) Finn Jacobs: 25% (Knowledge Acquisition)
5 | As a user I want to be able to delete entries from my bucket list so that I only see entries that resonate with me. | Add removed tag to entries or delete from phone and database-Create UI | 2--4 | Implement New Folder Modification Method | F(T) | 1 | 0.5 | Eli Story: 50% (Knowledge Acquisition) Brody Looney: 25% (Knowledge Acquisition) Callie Samson: 25% (Knowledge Acquisition) Finn Jacobs: 25% (Knowledge Acquisition)
16 | As a user I want to be able to add a deadline to an entry so that I am motivated to complete the task. | -Create UI-Research Notifications-Code Notifications-Create UI-Create deadline in entry class | 2--4 | Create a Deadline in the Entry Class | F(T, KA) | 1 | 1 | Eli Story: 100% (Knowledge Acquisition, Implementation) Brody Looney: 25% (Knowledge Acquisition) Callie Samson: 25% (Knowledge Acquisition) Finn Jacobs: 25% (Knowledge Acquisition)
7 | As a user I want to be able to sort my entries based on priority so that I know which entries I would like to complete first. | -Create UI-Add priority to entry class-Code sort- | 3--4 | Add Folder Modification, Implement Task Sorting System | F(T) | 2 | 0.25 | Eli Story: 30% (Knowledge Acquisition) Brody Looney: 30% (Knowledge Acquisition) Callie Samson: 20% (Knowledge Acquisition) Finn Jacobs: 20% (Knowledge Acquisition)
3 | As a user I want a folder for my completed entries so that I can keep track of what I have completed. | -Create UI for special Bucket -Create area in database for completed items | 4 | Create bucket where all completed items to to be seen | F(T) | 1 | 0.25 | Eli Story: 30% (Knowledge Acquisition) Brody Looney: 30% (Knowledge Acquisition) Callie Samson: 20% (Knowledge Acquisition) Finn Jacobs: 20% (Knowledge Acquisition)
8 | As a user I want to be able to see the number of active entries in the bucket list so that I can see how many entries there are for me to complete. | -Create UI - Count uncompleted tasks | 4 | Create UI to display number of active entries in Bucket | F(T) | 1 | 0 | Eli Story: 0% (Knowledge Acquisition) Brody Looney: 0% (Knowledge Acquisition) Callie Samson: 0% (Knowledge Acquisition) Finn Jacobs: 0% (Knowledge Acquisition)
9 | As a user I want to be able to see the number of completed entries in the bucket list so that I can track my progress. | -Create UI - Count completed tasks | 4 | Create UI to display number of completed entries in Bucket | F(T) | 1 | 0 | Eli Story: 0% (Knowledge Acquisition) Brody Looney: 0% (Knowledge Acquisition) Callie Samson: 0% (Knowledge Acquisition) Finn Jacobs: 0% (Knowledge Acquisition)