## Sheet1
ID | User Story | Sprint Number | Story Priority | Story Status | Story Points
1 | As a user I want to be able to create separate folders within the application so that I can put certain events/plans in specific categories. | 1--4 | H | D | 3
2 | As a user I would like to have a username and password for my application so that my information within the application is secure. | 1--2 | H | D | 2
3 | As a user I want a folder for my completed entries so that I can keep track of what I have completed. | 4--5 | M | IP | 1
4 | As a user I want to be able to have the option to share my bucket list with friends and other users of the application so that they can see my list. | 7 | L | W | 2
5 | As a user I want to be able to delete entries from my bucket list so that I only see entries that resonate with me. | 2--5 | H | D | 1
6 | As a user I want to be able to have the option to attach a picture with my entries so that I can have a visual representation of my entry. | 3--5 | L | IP | 3
7 | As a user I want to be able to sort my entries based on priority so that I know which entries I would like to complete first. | 3--4 | M | IP | 2
8 | As a user I want to be able to see the number of active entries in the bucket list so that I can see how many entries there are for me to complete. | 4--5 | L | IP | 1
9 | As a user I want to be able to see the number of completed entries in the bucket list so that I can track my progress. | 4--5 | L | IP | 1
10 | As a user I want to see popular entries from other users so that I can add these to my bucket list if I desire. | 8 | L | W | 2
11 | As a user I want the ability to set up a collaborative bucket list so that my friends or significant other can add things we wish to do together. | 7 | M | W | 3
12 | As a user I want to review how long it took me to complete the entry from the time I add it to when I check it off so that I can see how long it took me to complete the task. | 6 | L | W | 1
13 | As a user I want to be able to connect my account to other social media so that I can share my completed entries to other media platforms. | 8 | L | W | 3
14 | As a user I want to be able to set a profile picture so that I can stand out from other users. | 5 | L | IP | 1
15 | As a user I want to be able to change privacy settings on my account so that I can change what entries are visible to everyone/friends/only me. | 5 | M | IP | 2
16 | As a user I want to be able to add a deadline to an entry so that I am motivated to complete the task. | 2--5 | M | D | 1