## Sprint i
ID | User Story | Story Tasks | Sprint Number | Sprint Goal | Story Type | Story Points | Story Points Completed | Names and Contribution Percentage
7 | As a user I want to be able to sort my entries based on priority so that I know which entries I would like to complete first. | -Create UI-Add priority to entry class-Code sort- | 3--6 | Add Folder Modification, Implement Task Sorting System | F(T) | 2 | 0.25 | Eli Story: 30% (Knowledge Acquisition) Brody Looney: 30% (Knowledge Acquisition) Callie Samson: 20% (Knowledge Acquisition) Finn Jacobs: 20% (Knowledge Acquisition)
3 | As a user I want a folder for my completed entries so that I can keep track of what I have completed. | -Create UI for special Bucket -Create area in database for completed items | 4--6 | Create bucket where all completed items to to be seen | F(T) | 1 | 0.25 | Eli Story: 30% (Knowledge Acquisition) Brody Looney: 30% (Knowledge Acquisition) Callie Samson: 20% (Knowledge Acquisition) Finn Jacobs: 20% (Knowledge Acquisition)
8 | As a user I want to be able to see the number of active entries in the bucket list so that I can see how many entries there are for me to complete. | -Create UI - Count uncompleted tasks | 4--6 | Create UI to display number of active entries in Bucket | F(T) | 1 | 0.25 | Eli Story: 25% (Knowledge Acquisition) Brody Looney: 25% (Knowledge Acquisition) Callie Samson: 25% (Knowledge Acquisition) Finn Jacobs: 25% (Knowledge Acquisition)
9 | As a user I want to be able to see the number of completed entries in the bucket list so that I can track my progress. | -Create UI - Count completed tasks | 4--6 | Create UI to display number of completed entries in Bucket | F(T) | 1 | 0.25 | Eli Story: 25% (Knowledge Acquisition) Brody Looney: 25% (Knowledge Acquisition) Callie Samson: 25% (Knowledge Acquisition) Finn Jacobs: 25% (Knowledge Acquisition)
6 | As a user I want to be able to have the option to attach a picture with my entries so that I can have a visual representation of my entry. | -Create UI -Create icons -Upload icons | 3--6 | Create UI to display to pick one of the preset icons | F(T) | 3 | 0.5 | Eli Story: 25% (Knowledge Acquisition) Brody Looney: 25% (Knowledge Acquisition) Callie Samson: 25% (Knowledge Acquisition) Finn Jacobs: 25% (Knowledge Acquisition)
14 | As a user I want to be able to set a profile picture so that I can stand out from other users. | -Create UI -Upload Photos | 5--6 | Create location for user to change profile picture | F(T) | 1 | 0.25 | Eli Story: 25% (Knowledge Acquisition) Brody Looney: 25% (Knowledge Acquisition) Callie Samson: 25% (Knowledge Acquisition) Finn Jacobs: 25% (Knowledge Acquisition)
15 | As a user I want to be able to change privacy settings on my account so that I can change what entries are visible to everyone/friends/only me. | -Create UI -Create Privacy Settings | 5--6 | Create UI and code that allows user to update privacy settings on account | F(T) | 2 | 0.25 | Eli Story: 25% (Knowledge Acquisition) Brody Looney: 25% (Knowledge Acquisition) Callie Samson: 25% (Knowledge Acquisition) Finn Jacobs: 25% (Knowledge Acquisition)
12 | As a user I want to review how long it took me to complete the entry from the time I add it to when I check it off so that I can see how long it took me to complete the task. | -Create UI -Update item class | 6 | Create a timestamp in item class and store timestamp apon creation | F(T) | 1 | 0.15 | Eli Story: 15% (Knowledge Acquisition) Brody Looney: 15% (Knowledge Acquisition) Callie Samson: 15% (Knowledge Acquisition) Finn Jacobs: 15% (Knowledge Acquisition)